## Re-Entry
|  | STAY AT HOME |  | RE-OPEN PHASE 1 |  | RE-OPEN PHASE 2 |  | RE-OPEN 3
|  | March | April | May | June | July | August | September
Government | Federal Guidance | Nonessential businesses closed (at state discretion) Schools closed Gatherings of 10 people or less | Nonessential businesses closed (at state discretion) Schools closed Gatherings of 10 people or less | SCHOOLS AND ORGANIZED YOUTH ACTIVITIES (e.g., daycare, camp) that are currently closed should remain closed. LARGE VENUES (e.g., sit-down dining, movie theaters, sporting venues, places of worship) can operate under strict physical distancing protocols. |  | SCHOOLS AND ORGANIZED YOUTH ACTIVITIES (e.g., daycare, camp) can reopen. LARGE VENUES (e.g., sit-down dining, movie theaters, sporting venues, places of worship) can operate under moderate physical distancing protocols. |  | LARGE VENUES (e.g., sit-down dining, movie theaters, sporting venues, places of worship) can operate under limited physical distancing protocols.
| State Orders | Executive Order 2020-11 Nonessential state employees work from home, schools closed Executive Order 2020-17 Closed all nonessential businesses. | Executive Order 2020-21 Home or Work Order Executive Order 2020-28 ReOpens Retail Stores, Public beach access points, piers, docks, and wharfs. Schools remained closed through end of 2019-2020 school year. | Schools closed Large venues open (limited capacity 50 or less) | Daycare & camps open Large venues open (capacity increased 100-250) | Schools (colleges/univ), daycares & camps open Large venues of any size open | Schools (colleges/univ), daycares & camps open Large venues of any size open | Free for all
| Local Ordinances | Schools closed Nonessential businesses closed Social gatherings of 10 or more people prohibited Public beaches, piers, docs, wharfs, boat ramps and landings closed for recreation purposes Bars & restuarants pick, take-out or delivery only (no dine in/on premise consumption) | Schools closed Retail businesses reopen under capacity and safety protocol of county ordinance Public beaches open for exercise only (running, walking, surfing, biking). Sitting in chairs, sunbathing, loitering & congregations of 3 peop or more prohibited. | Schools closed Large venues open (limited capacity 50 or less) Beaches and parks open for recreation (group size limited) | Daycare & camps open Large venues open (capacity increased 100-250) Beaches and parks open for recreation (no size limit) | Schools (colleges/univ), daycares & camps open Large venues of any size open Beaches and parks open for recreation (no size limit) | Schools (colleges/univ), daycares & camps open Large venues of any size open Beaches and parks open for recreation (no size limit) | Free for all
Church | Wknd Experience | Online Wknd Exp | Online Wknd Exp | Online Wknd Exp | Online Wknd Exp Kickoff encouraging people to meet in person off campus in small #s for service watch parties with First Wed service | Online Wknd Exp (make move to stage for worship & teaching) | Begin Structured Wknd Exp | New Wknd Experience
| Kidscoast | Online Experience | Online Experience | Online Experience | Online Experience | Online Experience | Oncampus Ministry Begins | Open
| Custom | Online Experience | Online Experience | Online Experience | Online Experience | Online Experience | Oncampus Ministry Begins | Open
| Local Missions | Actively Serving at Select Campuses | Actively Serving at Select Campuses | Actively Serving Across All Campuses | Actively Serving Across All Campuses | Actively Serving Across All Campuses | Actively Serving Across All Campuses | Actively Serving Across All Campuses
| Small Groups | Online Groups | Online Groups | Online Groups | Meeting in Person | Meeting in Person | Meeting in Person | Meeting in Person
| Creative Support | At Home & On the Go | At Home & On the Go | Promo Jun First Wed & Kickoff of Encouraging People to Meet in Homes/In Person Offcampus | 1. Continued encouragement of meeting in person in small groups 2. July on campus prayer and worship events | 1. Continued promo of oncampus prayer & worship events 2. August oncampus Wknd Exp 3. NextGen environments and protocols | 1. Oncampus Wknd Exp 2. NextGen
Usage and Staff Expectation | Building Usage |  | 1. Closed to outside groups 2. Offices Closed 3. Essential Staff Only Groups limited to no more than 10, but multiple groups within the building at one time if they are working or using different parts of the building. Limited hours during filming. 4. Protective gear available including gloves and masks. 5. Social distancing requirements with at least 6 feet between you and others 6. One restroom open 7. Conserve our utilities costs | 1. Closed to large outside groups, Groups under 10-50 or other mandated guideline # need Exec Group approval. 2. Offices Closed 3. Essential Staff Only Groups limited to no more than 50, but multiple groups within the building at one time if they are working or using different parts of the building. Limited hours during filming. 4. Protective gear available including gloves and masks. 5. Social distancing requirements with at least 6 feet between you and others 6. One restroom open 7. Conserve our utilities costs | 1. Closed to large outside groups, Groups under 100 or other mandated guideline # need Exec Group approval. 2. Offices Potentially Open 3. Protective gear available - masks. 4. Social distancing requirements with at least 6 feet between you and others 5. One restroom open 6. Conserve our utilities costs | 1. Building Opens Limited groups 250-500 or other mandated guideline Wkly Prayer or Worship Gatherings Across All Campuse 2. Offices Open 3. Protective gear available - masks. | 1. Building Opens No restrictions 2. Offices Open 3. Protective gear available - masks.
| Staff Expectations | April: 1. Remote work for the majority of staff, some essential staff needed on-site (filming; maintenance, etc). 2. Report COVID-19 related symptoms, do not work on site with any concerning symptoms or if a family member is experiencing concerning symptoms. 3. Mandatory Quarantine/OffSite for 2 weeks for those in contact with a positive COVID case; May: 1. Remote work for the majority of staff, some essential staff needed on-site (filming; maintenance, etc). 2. Report COVID-19 related symptoms, do not work on site with any concerning symptoms, or if a family member is experiencing concerning symptoms. 3. Mandatory Quarantine/Offiste for 2 weeks for those in contact a positive COVID case; June: 1. In-Office Optional except for essential staff needed on-site (filming, maintenance, or potentially for services) Remote work available, especially for high risk staff and as needed on a case by case basis 2. Report COVID-19 related symptoms, do not work on site with any concerning symptoms or if a member in your family is experiencing concerning symptoms 3. Mandatory Quarantine/Offsite for 2 weeks for those in contact with a positive COVID case 4. Face Mask Required in close-proximity to others in Office and Large-group services; July: 1. Offices Open, all staff encouraged to return, but Remote work for high risk staff is available 2. Report COVID-19 related symptoms, do not work on site with any concerning symptoms or if a member in your family is experiencing concerning symptoms. 3. Face Mask Optional?
| Budget Restrictions |  | All Nonessential Spending Cut, all purchases above $1000 approved by Nick/Margaret Not Approved: Travel, Employee Appreciation, food, subscriptions, books, etc. Limited Approval: Ministry expenses, advertising, contract labor Hiring Freeze in effect | All Nonessential Spending Cut: All purchases above $1000 approved by Nick/Margaret Not Approved: Travel, food, subscriptions, books, etc. Limited Approval: Employee Appreciation, Ministry expenses, advertising, contract labor Hiring Freeze in effect | TBD | TBD | TBD | TBD

## Campus Capacity
Campus | Capacity | 20% | 50% | 75%
AVL | 245 | 49 | 122.5 | 183.75
COL | 244 | 48.8 | 122 | 183
CON | 264 | 52.8 | 132 | 198
GVL | 195 | 39 | 97.5 | 146.25
IRM | 550 | 110 | 275 | 412.5
JHN | 275 | 55 | 137.5 | 206.25
JMS |  | 0 | 0 | 0
MCC | 96 | 19.2 | 48 | 72
MNG | 350 | 70 | 175 | 262.5
MTP (WC) | 2525 | 505 | 1262.5 | 1893.75
MTP (SC) | 1325 | 265 | 662.5 | 993.75
MTP (Chapel) | 225 | 45 | 112.5 | 168.75
MTP (WH) | 325 | 65 | 162.5 | 243.75
NCH | 250 | 50 | 125 | 187.5
SVL | 490 | 98 | 245 | 367.5
WST | 570 | 114 | 285 | 427.5